## Gantt Chart
Gantt Chart
TITLE: Plant Pals Operations and Training Plan | [6 empty] | COMPANY NAME: |  |  |  |  | Office Green
PROJECT MANAGER: [Name] | [6 empty] | CREATION DATE: |  |  |  |  | 02/15
TASK ID NUMBER | MILESTONES & TASKS | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [29 empty] | PHASE TWO | [14 empty] | PHASE THREE
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | MARCH | [22 empty] | APRIL | [21 empty] | MAY | [20 empty] | JUNE
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Establish a plant delivery and logistics plan | [5 empty] | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11
1.1 | Source packaging materials | Fulfillment Director | 3/1 | 3/12 | 10 | 0% | bar: MARCH M 1 to MARCH F 12
1.2 | Hire delivery drivers | Human Resources Specialist | 3/15 | 3/26 | 10 | 0% | bar: MARCH M 15 to MARCH F 26
1.3 | Calculate the delivery fees | Financial Analyst | 3/29 | 4/9 | 10 | 0% | bar: MARCH M 29 to APRIL F 9
2 | Select and install supply chain software and equipment
2.1 | Set up systems for inventory management and fulfillment | Inventory Manager | 4/12 | 4/14 | 3 | 0% | bar: APRIL M 12 to APRIL W 14
2.2 | Oversee the installation of the fulfillment equipment | Inventory Manager | 4/15 | 4/16 | 2 | 0% | bar: APRIL R 15 to APRIL F 16
2.3 | Establish safety protocols and practices for the equipment | Quality Assurance Tester | 4/19 | 4/30 | 10 | 0% | bar: APRIL M 19 to APRIL F 30
3 | Develop and launch an employee training program
3.1 | Develop communication plan | Human Resources Specialist | 5/3 | 5/14 | 10 | 0% | bar: MAY M 3 to MAY F 14
3.2 | Develop the employee training program | Training Manager | 5/17 | 5/28 | 10 | 0% | bar: MAY M 17 to MAY F 28
3.3 | Train Office Green employees to use the software and equipment | Training Manager | 5/31 | 6/11 | 10 | 0% | bar: MAY M 31 to JUNE F 11